## English
EASTERN INTERNATIONAL UNIVERSITY
SCHOOL OF COMPUTING AND INFORMATION TECHNOLOGY
THE PROGRESS TRACKING OF INTERNSHIP PROJECT
NAME COURSE: |  |  |  | CODE COURSE: | CSE 412
PROJECT NAME: |  |  |  | DEPT: | 3 months ( 16/06 - 16/09 )
SUPERVISOR: |  | Phan Văn Vinh
STUDENTS (NAME - ID NUMBER - PHONE NUMBER):
1/ | Hà Quang Minh | 1931220012 | 961617415
2/
3/
Link github : https://github.com/HaQuangMinhh/Internship-Athena
No | TIME | STUDENT'S TASKS HAS DONE | STUDENT'S SIGNATURE | SUPERVISOR'S COMMENTS | REMARKS
1 | WEEK1 | 1/ Study the theory of network management – its roles, objectives, and challenges.
| From 16/06 | 2/ Research basic infrastructure components: switches, routers, firewalls, servers.
| To 22/06 | 3/ Create a basic sample network topology for an enterprise.
2 | WEEK 2 | 1/ Study GCP’s VPC, Subnet, Firewall rules, and Cloud Router.
| From 23/06 | 2/ Set up a GCP project and configure a basic virtual network.
| To 30/06 | 3/ Document costs, free tier limits, and security considerations.
3 | WEEK 3 | 1/ Explore AWS VPC, Subnets, Route Tables, and Security Groups.
| From 1/7 | 2/ Deploy a demo VPC with EC2 instances to trace network flow.
| To 7/7 | 3/ Compare AWS and GCP from a network management perspective.
4 | WEEK 4 | 1/ Research VNet, Network Security Groups, and Azure Bastion.
| From 8/7 | 2/ Create a sample network with Azure VM and VNet.
| To 14/7 | 3/ Compare Azure with GCP and AWS.
5 | WEEK 5 | 1/ Analyze requirements for security, performance, and user access.
| From 15/7 | 2/ Create documentation for hardware, software, and cloud resource needs.
| To 21/7 | 3/ Simulate a network diagram for enterprise network administration.
6 | WEEK 6 | 1/ Install and configure VMware.
| From 22/7 | 2/ Import IP schema, devices, and topology into VMs.
| To 28/7 | 3/ Manage network devices and configure VLANs.
7 | WEEK 7 | 1/ Study Ansible or Terraform for automated network configuration.
| From 29/7 | 2/ Write an Ansible playbook for IP/VLAN setup and backup.
| To 4/8 | 3/ Integrate NetBox with Ansible for dynamic configuration input.
8 | WEEK 8 | 1/ Contact technicians or use simulated Athena data.
| From 5/8 | 2/ Draw a realistic or close-replica network diagram of Athena.
| To 11/8 | 3/ Assess current network management efficiency and identify weaknesses.
9 | WEEK 9 | 1/ Redesign Athena’s network system with enhanced manageability.
| From 12/8 | 2/ Build a NetBox instance representing Athena’s infrastructure.
| To 18/8 | 3/ Propose transition to cloud or hybrid network model if applicable.
10 | WEEK 10 | 1/ Write a comprehensive report covering Weeks 1–9.
| From 19/8 | 2/ Prepare presentation slides.
| To 25/8 | 3/ Receive and integrate mentor/instructor feedback.